Geyser Controller Deployment Timeline (For first 5 Units)

Step 1: Procurement of components (First 5 units) - Complete

Step 2: Assembly (1 day per controller)

- 1st controller: Complete

Step 3: Software Integration and Deployment (3 days)

- Flash OS and setup, cert generation etc (1 day) - Complete

- Configure Json files, set up IV meter etc (0.5 days) - Complete

- Successfully clone repository, set up virtual environment and deploy code (0.5 days) - In Progress

- Verify Thingsboard connectivity, test telemetry and remote commands (1 day)

Step 4: Testing and Validation of Controller (5 days)

- Functional Testing  - IV meter, LEDs etc (1 day)

- Safety Tests – Simulate HW faults, over temp protection etc. (2 days)

- Network Testing – Wifi provisioning, data uploads etc. (2 days)

Step 5: Replication for remaining 4 controllers

- Repeat (Step 2 - 4) for 4 other controllers with Jamie

- Parallelize Assembly + SW integration and Deployment + Testing

Step 6: Final Review & Handover (1 day)

- Final System check (0.5 days)

- Handover to Installers (0.5 days)

Total Estimated Timeline:

Ideal Timeline

- First Controller, fully tested and ready (10 days)

- Assembly Documentation (1 day)

- Installation Documentation (1 day)

- Documentation of deployment process (1 day)

- Testing Documention (1 day)

- Repeat for 4 other controller (12 days)

Total: 26 working days

Probable Timeline

- First Controller, fully tested and ready (26 days)

- Assembly Documentation (2 days)

- Installation Documentation (2 days)

- Documentation of deployment process (2 days)

- Testing Documention (2 days)

- Repeat for 4 other controller (31 days)

Total: 65 working days

Recommendations:
I spoke with Louis Van Rooyen. He is the previous designer/developer of the hardware and software for the geyser controller. He said he would be available as a consultant to help finish off the project. His rate is R550 per hour (might be negotiable).

I would STRONGLY recommend making use of Louis, mainly for the first 5 units. Once the first 5 are completed, the remaining 25 is just replication. Why?

- Fault Finding:
Louis can quickly diagnose and fix integration issues that would take hours or days for me to resolve. (This has been one of my biggest delays so far)

- Proper Knowledge Transfer:
Before I was not at all involved with this progress. When Louis before Louis left, I had 1x 1 hour session to figure out what is going on and what I need to do. Despite making somewhat decent and in all honesty slow progress, I believe working alongside Louis will further accelerate my understanding of the system, enabling me to independently manage future deployments and troubleshooting in the future.

- Timeline and Safety Issues:
Since this is a critical project, relying solely on my learning curve risks delays and potential mistakes. I am learning and figuring things out along the way especially due to the somewhat complex nature in which the project was set up. Since this is a time sensitive project with potential safety issues due to the system being used with customers working systems, I believe he should be onboarded.

- Efficient Use of Resources:
Louis’s consulting fee is justified by the time saved and the avoidance of costly errors or reworks. His involvement ensures the first 5 units are deployed correctly, setting a solid foundation for scaling up to the next 25 units.

- Mentorship:
Having Louis involved allows for real time mentorship and the creation of robust documentation and processes for future installations.

Total Estimated Timeline (With Louis as a Consultant):

Estimated Timeline

- First Controller, fully tested and ready (8 days)

- Assembly Documentation (1 day)

- Installation Documentation (1 day)

- Documentation of deployment process (1 day)

- Testing Documentation (1 day)

- Repeat for 4 other controller (12 days)

Total: 24 working days